## Sheet1
Project Logs
Date | Name | Task
2023-07-08 | Arshneet | Sent git invitation to all the members
2023-07-10 | Vikas | Worked on Wire Frame
2023-07-11 | Rishabh | Worked on site map
2023-07-11 | Pranjal | researched on color theme
2023-07-12 | Arshneet | Worked on home page
2023-07-24 | Pranjal | created color theme
2023-07-24 | Rishabh | Worked on the movie page
2023-07-27 | Pranjal | Collected and integrated media and other relevant data
2023-07-27 | Vikas | worked on wireframe
2023-07-27 | Rishabh | styling of video rendering page
2023-07-27 | Arshneet | worked on FAQ page
2023-07-29 | Rishabh | Worked on contact us page
2023-07-29 | Pranjal | Worked on company logo and favicon
2023-07-29 | Vikas | modified movie page
2023-07-29 | Arshneet | Completed home page
2023-07-30 | Pranjal | Worked on about us page
2023-07-30 | Rishabh | Completed contactus page
2023-07-30 | Arshneet | completed Faq page
2023-07-02 | Vikas | did changes in responsiveness of home page
2023-07-02 | Pranjal | Completed about us pages
2023-07-02 | Rishabh | worked on documentation
2023-07-02 | Arshneet | worked on documentation